## Sheet1
task | subtask | duration | label | before | after | start | end | responsible
.
phase | phase | 36 | PFP | FP |  |  |  | IO
phase | phase | 18 | FP | PFPO1 |  |  |  | IO
phase | phase | 18 | PFPO1 |  |  | 2028-12-01 |  | IO
phase | phase | 21 | PFPO2 |  | PFPO1 |  |  | IO
phase | phase | 24 | FPO1 |  | PFPO2 |  |  | IO
phase | phase | 24 | FPO2 |  | FPO1 |  |  | IO
phase | phase | 24 | FPO3 |  | FPO2 |  |  | IO
.
vacuum field | task |  | vf |  |  |  |  | DIS,SCOD
| as-built coil cage geometric data available (TFC, PFC, CS) | -24 | ms-coildata |  | PFP |  |  | DIS
| simulate operational TF coil cage shape | 3 | tfopp |  | ms-coildata |  |  | SCOD
| built 3D field maps + check toroidal field symmetry | 9 | baseline-map3d |  | tfopp |  |  | SCOD
| as-built correction coil geometric data available | 9 | ms-ccf | FP
| built 3D correction coil field maps + check corrected field symmetry | 9 | cc-coil-map3d |  | ms-ccf |  |  | SCOD
| as-built ELM coil data available | 12 | ms-elmf |  | FP
| built 3D ELM coil field maps | 9 | elm-coil-map3d |  | ms-elmf |  |  | SCOD
.
synthetic diagnostics | task |  | sdiag
| FP diagnostic forward models | 16 | sdiag-FP |  |  |  | 2022-04-01
| PFPO1 diagnostic forward models | 18 | sdiag-PFPO1 | FP
| PFPO2 diagnostic forward models | 18 | sdiag-PFPO2 | PFPO1
| full set of synthetic diagnostics available | 0 | ms-sdiag |  | sdiag-PFPO2
.
diagnostic feed pre-processing | task |  | diag |  |  |  |  | IVD
| validate / develop magnet commissioning waveforms | 9 | diag-wf | FP
| magnetics-only + interferometer available | 6 | ms-mag-only |  | PFP |  |  | IVD
| magnetics-only + interferometer inference | 9 | mag-only-bay | PFPO1 | ms-mag-only,tfopp,fm-dipole |  |  | SCOD
| (DIP, TIP, TS core <80%) available | 6 | ms-kinetic1 |  | FP |  |  | IVD
| initial kinetic inference | 9 | kinetic1-bay | PFPO2
| (PoPola, MSE-LS, TS edge, Reflectometry) available | 9 | ms-diag-full |  | PFPO1
| full baseline inference | 6 | diag-full-bay | FPO1 | ms-diag-full
| develop commissioning waveforms to target TBMs | 12 | wm-wf-tbm | PFPO2
| re-calibrate diagnostics following TBM installation | 9 | diag-full-tbm |  | wm-wf-tbm
| full baseline diagnostics inference + TBM | 6 | diag-full-tbm-bay |  | fm-dipole-tbm
| full baseline diagnostics + TBMs available | 0 | ms-full-diag-tbm |  | diag-full-tbm-bay
.
linear reconstruction | task |  | lr
| adapt existing 2D codes to IMAS | 6 | lin-code2d |  |  | 2022-01-01
| develop benchmark and quality metrics | 3 | lin-metric |  | lin-code2d
| benchmark (mag-only) | 6 | lin-bm-mag |  | lin-code2d,sdiag-FP,lin-metric |  |  | F4E
| benchmarked real-time codes available on SDCC | 0 | ms-lin-code2d-bm |  | lin-bm-mag
| benchmark (mag + initial kinetic) | 6 | lin-bm-initial-kinetic |  | lin-code2d,sdiag-PFPO1,lin-bm-mag
| benchmark (full diagnostic baseline) | 9 | lin-bm-full |  | lin-code2d,sdiag-PFPO2,lin-bm-initial-kinetic
| benchmark (other tokamaks, full diagnostic baseline) | 9 | lin-bm-full-real |  | lin-bm-full
| select real-time 2D reconstruction code and make available on SDCC | 0 | ms-lin-code-rt2d |  | lin-bm-full-real
| check existing code convergence (mag constraint / shifted grids) | 3 | lin-conv |  | lin-bm-full-real
| code refactoring to improve performance and physics fidelity | 6 | lin-refactor |  | lin-conv
| adapt existing 3D codes to IMAS | 9 | lin-code3d | PFPO2 |  |  |  | SCOD
| 3D reconstruction codes available on SDCC | 0 | ms-lin-code3d |  | lin-code3d
.
ferritic model | task |  | fm
| extend IMAS data dictionary to represent ferritic structures | 3 | fm-imas | fm-geom
| implement ferritic insert geometry in IMAS | 3 | fm-geom |  |  | 2021-08-01
| develop dipole representation (fast, far-field) | 9 | fm-dipole |  | fm-geom
| update insert geometry from measurements | 6 | fm-bay | mag-only-bay
| ferritic insert model available | 0 | ms-ferritic-inserts |  | fm-bay
| implement ferritic TBM geometry in IMAS | 6 | fm-tbm | PFPO2
| extend dipole representation to include TBMs | 12 | fm-dipole-tbm |  | fm-tbm
| update TBM geometry from measurements | 9 | fm-tbm-bay |  | fm-dipole-tbm,diag-full-tbm
| ferritic TBM model available | 0 | ms-ferritic-tbm |  | fm-tbm-bay
.
wall model | task |  | wm
| develop 2D model (eddy current) | 9 | wm-2d-eddy |  | fm-dipole
| validate 2D model using Alcator-C mod data | 6 | wm-2d-val |  | wm-2d-eddy,sdiag-FP
| validate / develop 2D magnet commissioning waveforms | 3 | wm-wf | FP
| measure open-loop vessel response (2D model) | 6 | wm-ol |  | wm-wf,ms-mag-only
| tune 2D wall model | 6 | wm-2d-cal |  | wm-ol
| slow transient 2D model available | 0 | ms-wm-2d-slow |  | wm-2d-cal
| tune model to fit disruption behaviour (low current) | 9 | wm-disrupt-low |  | FP,wm-2d-cal
| fast transient 2D model available | 0 | ms-wm-2d-fast |  | wm-disrupt-low
| develop 2D shield-block models | 9 | wm-shield | wm-disrupt-half
| tune model to fit disruption behaviour (half current) | 3 | wm-disrupt-half | PFPO2
| fast transient 2D model available + shield-blocks | 0 | ms-wm-2d-fast-shield |  | wm-disrupt-half
| develop 3D wall model (eddy current ) | 18 | wm-3d-eddy | wm-3d-val
| validate 3D wall model on Alcator-C mod data | 6 | wm-3d-val | wm-wf-3d
| validate / develop 3D magnet commissioning waveforms (ELM) | 3 | wm-wf-3d | wm-ol-3d
| measure open-loop vessel response (3D model) | 6 | wm-ol-3d | PFPO2
| tune 3D wall model | 6 | wm-3d-cal |  | wm-ol-3d
| fast transient 3D model available | 0 | ms-wm-3d |  | wm-3d-cal
| develop 3D shield-block models | 9 | wm-shield-3d |  | wm-3d-cal
| tune 2D and 3D models to fit disruption behaviour (full current) | 6 | wm-ol-3d-fast |  | wm-shield-3d
| fast transient 3D model available + shield-blocks | 0 | ms-wm-ol-3d |  | wm-ol-3d-fast
.
stability analysis | task |  | sta
| calculate positions of low-n rational surfaces | 6 | sta-rational |  | ms-lin-code-rt2d
| validate positions of low-n rational surface on RTN | 3 | sta-rational-val |  | sta-rational
| calculate proximity to ideal low-n linear stability in 2d equilibrium | 9 | sta-proxy-2d |  | lin-conv
| baseline low-n stability metrics available | 0 | ms-sta-low-n |  | sta-proxy-2d
| establish need for automatic stability post-processing vs user-triggered | 6 | sta-automatic |  | ms-sta-low-n
| calculate resistive low-n stability (NTMs) | 12 | sta-NTMs |  | ms-ferritic-inserts,ms-wm-3d,PFPO1
| establish need to provide information on other stability boundaries | 9 | sta-other |  | sta-NTMs
| establish if routine high-n peeling / ballooning stability is viable / required | 6 | sta-high-n |  | lin-code3d,PFPO2,sta-other
| calculate high-n peeling / ballooning stability (ELMs) | 9 | sta-ELMs |  | elm-coil-map3d,sta-high-n
| assess need for higher-n calculations of AE modes (advanced control) | 9 | sta-AE | sta-proxy-3d
| calculate proximity to ideal low-n linear stability in 3d equilibrium | 18 | sta-proxy-3d | FPO3
.
transport model | task |  | tm
| constrain 2D equilibrium with 1D transport model | 9 | tm-trans2d | tm-trans2d-forw
| benchmark 2D equilibrium + 1D transport model | 6 | tm-trans2d-forw | ms-trans2d
| coupled 2D equilibrium + 1D transport model available | 0 | ms-trans2d | pkm-mag2d
| constrain 3D equilibrium with 1D transport model | 18 | tm-trans3d | tm-trans3d-forw
| benchmark 3D equilibrium + 1D transport model | 6 | tm-trans3d-forw | pekm-full3d
| coupled 3D equilibrium + 1D transport model available | 0 | ms-trans3d |  | tm-trans3d-forw
.
plasma state estimation | task |  | pkm
| develop Kalman filters for plasma (mag-only 2D) | 6 | pkm-mag2d | PFPO1
| develop Kalman filters for plasma (mag-only + initial kinetic 2D) | 9 | pkm-initial-kinetic2d | PFPO2
| develop Kalman filters for plasma (full diagnostics 2D) | 6 | pkm-full2d |  | pkm-initial-kinetic2d
| implement full state-aware model (plasma+passive, 2D) | 3 | pkm-2d |  | pkm-full2d
| 2D plasma Kalman filter available | 0 | ms-pkm2d |  | pkm-2d
| establish operation with switched diagnostics (DNB duty cycle) | 9 | pkm-dnb |  | ms-pkm2d
| develop ensemble Kalman filters for plasma (3D) | 18 | pekm-full3d | pekm-3d
| implement full state-aware model (plasma+passive, 3D) | 6 | pekm-3d | ms-pekm3d
| 3D plasma Kalman filter available | 0 | ms-pekm3d | FPO1
.
interface to engineering | task |  | eng
| define interfaces to ensure timely propagation of EM data | 3 | eng-data | FP
| calculate forces on EM components (coils, feeders, vessel, sieldblocks) | 6 | eng-force |  | eng-data
| baseline engineering data available | 0 | ms-eng-baseline |  | eng-force
| calculate dBdt waveforms along all superconducting paths (includes disruptions) | 9 | eng-dBdt | PFPO1 | wm-disrupt-half
| calculate lifetime consumption of EM components (fatigue) | 12 | eng-fatigue |  | eng-force,eng-dBdt
| interface with inductive compensator used by quench detection system | 9 | eng-qd | PFPO2 | eng-dBdt
| develop full-pulse reconstructions (pre/post plasma) to inform AC-loss calculations | 18 | eng-full-pulse |  | ms-pkm2d
| full-set of engineering data available | 0 | ms-eng-full |  | eng-full-pulse
.
non-linear reconstruction | task |  | nlr
| define minimization objective(s) (minimum free-energy) | 6 | nlr-obj | PFPO1
| develop generic parametrizations (flux functions) | 9 | nlr-param |  | nlr-obj
| refactor non-linear search for real-time (ML model) | 18 | nlr-refactor |  | nlr-param
| couple non-linear search algorithms (optimizers) to 2D code | 9 | nlr-opp-2d |  | nlr-refactor
| commission 2D non-linear reconstruction | 6 | nlr2d |  | nlr-opp-2d
| non-linear 2D reconstructions available | 0 | ms-nlr2d |  | nlr2d
| couple non-linear search algorithms (optimizers) to 3D code | 3 | nlr-opp-3d |  | ms-lin-code3d,ms-nlr2d
| commission 3D non-linear reconstruction | 6 | nlr3d |  | nlr-opp-3d
| non-linear 3D reconstructions available | 0 | ms-nlr3d |  | nlr3d