## Sheet1
task | subtask | assignment | duration | label | before | after | start | end | responsible
phase | assembly | phase | 51 | A-I | IC-I
phase | integrated commissioning |  | 14 | IC-I | FP+EO
phase | phase |  | 6 | FP+EO |  |  | 2028-12-01
phase | assembly |  | 24 | A-II |  | FP+EO
phase | integrated commissioning |  | 6 | IC-II |  | A-II
phase | phase |  | 18 | PFPO-1 |  | IC-II
phase | assembly |  | 15 | A-III |  | PFPO-1
phase | integrated commissioning |  | 9 | IC-III |  | A-III
phase | phase |  | 21 | PFPO-2 |  | IC-III
phase | assembly |  | 13 | A-IV |  | PFPO-2
phase | integrated commissioning |  | 8 | IC-IV |  | A-IV
phase | phase |  | 16 | FPO-1 |  | IC-IV
phase | shutdown |  | 8 | SD-I |  | FPO-1
phase | phase |  | 16 | FPO-2 |  | SD-I
phase | shutdown |  | 8 | SD-II |  | FPO-2
phase | phase |  | 16 | FPO-3 |  | SD-II
phase | shutdown |  | 9 | SD-III |  | FPO-3
phase | phase |  | 16 | FPO-4 |  | SD-III
phase | shutdown |  | 8 | SD-IV |  | FPO-4
phase | phase |  | 16 | FPO-5 |  | SD-IV
phase | shutdown |  | 4 | SD-V |  | FPO-5
phase | phase |  | 16 | FPO-6 |  | SD-V
.
equilibrium generation | task | equilibrium reconstruction |  | eg
| identify and develop IMAS equilibrium tools (flux mapping and transforms) |  | 6 | nova-map | nova
| adapt in-house 2D free-boundary GS solver to IMAS |  | 6 | nova | A-I
| FP diagnostic forward models available |  | 0 | ms-sdiag-FP | A-I
| verify implementation of in-house 2D solver against external codes |  | 3 | nova-2D-verify |  | nova
| in-house free-boundary equilibrium solver available |  | 0 | ms-nova-2D |  | nova-2D-verify
| develop in-house 3D free-boundary GS solver |  | 12 | nova-3D-GS |  | lin-bm-initial-kinetic
| verify implementation of in-house 3D solver against external codes |  | 3 | nova-3D-GS-verify |  | nova-3D-GS
| 3D in-house free-boundary equilibrium solver available |  | 0 | ms-nova-3d |  | nova-3D-GS-verify
.
linear reconstruction | task |  |  | lr
| PFPO-1 diagnostic forward models available |  | 0 | ms-sdiag-PFPO-1 | A-II
| develop in-house equilibrium reconstruction using FP synthetic diagnostics |  | 6 | lr-nova-fp |  | ms-nova-2D
| implement provision of synthetic diagnostics via IO's DAN |  | 3 | sdiag-DAN |  | lr-nova-fp
| demonstrate FP equilibrium reconstruction pipeline on SDCC using DAN data |  | 3 | lr-nova-fp-demo |  | sdiag-DAN
| in-house linear equilibrium reconstruction pipeline available |  | 0 | ms-nova-DAN |  | lr-nova-fp-demo
| develop benchmarks and quality metrics |  | 3 | lin-metric |  | ms-nova-DAN
| benchmark (synthetic mag-only) |  | 6 | lin-bm-mag |  | lin-metric |  |  | F4E
| benchmarked low-latency equilibrium regression pipeline available on SDCC |  | 0 | ms-nova-bm |  | lin-bm-mag
| carry out equilibrium reconstructions in support of FP |  | 6 | lin-fp-support |  | IC-I
| code improvement and refactoring following lessons learnt from FP operations |  | 3 | lin-refactor |  | lin-fp-support
| extend in-house code to use vv structural diagnostics (vessel strain and displacement) |  | 6 | lin-strain-nova |  | ms-nlr2d
| develop in-house equilibrium reconstruction using PFPO1 synthetic diagnostics |  | 6 | lr-nova-pfpo1 |  | ms-sdiag-PFPO-1,lin-refactor
| demonstrate PFPO-1 equilibrium reconstruction pipeline on SDCC using DAN data |  | 3 | lr-nova-pfpo1-demo |  | lr-nova-pfpo1
| benchmark (synthetic mag-only + initial kinetic) |  | 3 | lin-bm-initial-kinetic |  | lr-nova-pfpo1-demo
| carry out equilibrium reconstructions in support of PFPO-1 |  | 6 | nl-pfpo1-support |  | kinetic1
| carry out equilibrium reconstructions in support of PFPO-2 |  | 6 | nl-pfpo3-support |  | diag-full
.
non-linear reconstruction | task |  |  | nlr
| define minimization objective(s) (minimum free-energy) |  | 3 | nlr-obj |  | ms-nova-bm
| develop non-linear parametrizations (extend flux functions - include rotation & fast ions) |  | 3 | nlr-param |  | nlr-obj
| refactor non-linear search for low-latency regression (ML model) |  | 6 | nlr-refactor |  | nlr-param
| couple non-linear search algorithms (optimizers) to 2D code |  | 6 | nlr-opp-2d |  | nlr-refactor
| demonstrate in-house non-linear equilibrium reconstruction pipeline on SDCC |  | 3 | nlr2d |  | nlr-opp-2d
| non-linear 2D reconstructions available |  | 0 | ms-nlr2d |  | nlr2d
| carry out equilibrium reconstructions in support of PFPO-1 |  | 6 | nlr-pfpo1-support |  | nl-pfpo1-support
| code improvement and refactoring following lessons learnt from PFPO-1 operations |  | 3 | nlin-refactor |  | nlr-pfpo1-support
| PFPO-2 diagnostic forward models available |  | 0 | ms-sdiag-PFPO-2 | A-III
| develop in-house equilibrium reconstruction using PFPO-2 synthetic diagnostics |  | 6 | lr-nova-pfpo2 |  | nlin-refactor,ms-sdiag-PFPO-2
| demonstrate PFPO-2 equilibrium reconstruction pipeline on SDCC using DAN data |  | 3 | lr-nova-pfpo2-demo |  | lr-nova-pfpo2
| benchmark (synthetic full diagnostic baseline) |  | 6 | lin-bm-full |  | lr-nova-pfpo2-demo
| carry out equilibrium reconstructions in support of PFPO-2 |  | 9 | nlr-pfpo3-support |  | nl-pfpo3-support
.
diagnostic data | task |  |  | dd
| magnetics-only diagnostics available |  | 0 | ms-mag-only |  | A-I
| develop commissioning waveforms to target magnetics diagnostics |  | 3 | mag-wf |  | A-I
| implement magnetics data processing pipeline (clean, check and archive) |  | 2 | mag-clean |  | mag-wf
| characterize magnetics measurements (3D vacuum field + mag axis offset) |  | 9 | mag-only-vacuum |  | mag-clean |  |  | SCOD
| (DIP, TIP, TS core r/a<85%) diagnostics available |  | 0 | ms-kinetic1 |  | IC-II |  |  | IVD
| implement kinetic data processing pipeline (clean, check and archive) |  | 3 | kinetic-clean |  | ms-kinetic1
| characterize kinetic measurements |  | 3 | kinetic1 |  | kinetic-clean
| develop commissioning waveforms to target TBM characterization |  | 3 | wm-wf-tbm |  | lin-bm-full
| re-calibrate magnetic diagnostics following TBM installation (3D vacuum field) |  | 3 | diag-3d-tbm |  | wm-wf-tbm
| (PoPola, MSE-LS, TS edge, Reflectometry) available |  | 0 | ms-diag-full | PFPO-2
| implement full baseline diagnostic data processing pipeline (clean, check and archive) |  | 3 | diag-full-clean |  | ms-diag-full
| characterize full diagnostic baseline (excl. neutronics) |  | 3 | diag-full |  | diag-full-clean
.
ferritic model | task | machine characterisation |  | fm
| extend IMAS data dictionary to represent ferritic structures |  | 3 | fm-imas |  |  | 2022-08-01
| implement ferritic insert geometry in IMAS |  | 3 | fm-geom |  | fm-imas
| develop dipole representation (fast, far-field) |  | 6 | fm-dipole |  | fm-geom
| implement ferritic TBM geometry in IMAS |  | 3 | fm-tbm |  | fm-dipole
| extend dipole representation to include TBMs |  | 3 | fm-dipole-tbm |  | fm-tbm
| tune ferritic insert model from vacuum field measurements |  | 3 | fm-bay |  | wm-CS-ramp
| tune TBM geometry from field measurements |  | 9 | fm-tbm-bay | PFPO-2
.
wall model | task |  |  | wm
| develop 2D model (eddy current) |  | 3 | wm-2d-eddy |  | fm-dipole-tbm
| tune 2D wall model using 3D vessel CS ramp and disruption simulations |  | 3 | wm-2d-tune |  | wm-2d-eddy
| validate 2D model using Alcator-C mod experimental data |  | 3 | wm-2d-val |  | wm-2d-tune
| develop 2D commissioning waveforms |  | 6 | wm-wf |  | wm-2d-val
| develop 3D wall model (eddy current ) |  | 9 | wm-3d-eddy |  | wm-wf
| validate 3D wall model on Alcator-C mod experimental data |  | 3 | wm-3d-val |  | wm-3d-eddy
| develop 3D commissioning waveforms (ELM) |  | 3 | wm-wf-3d |  | wm-3d-val
| measure open-loop vessel response (PF, CS) |  | 3 | wm-ol |  | vf-magaxis
| tune 2D wall model |  | 3 | wm-2d-cal |  | wm-ol
| tune model to fit CS ramp |  | 3 | wm-CS-ramp |  | wm-2d-cal
| develop 2D shield-block models |  | 3 | wm-shield |  | fm-bay
| develop 3D shield-block models |  | 6 | wm-shield-3d |  | wm-shield
| develop 3D commissioning waveforms |  | 3 | wm-wf-shield-3d |  | fm-tbm-bay
| measure open-loop vessel response (3D model) |  | 3 | wm-ol-3d |  | wm-wf-shield-3d
.
vacuum field | task |  |  | vf |  |  |  |  | DIS,SCOD
| as-built coil geometric data available (TFC, PFC, CS, CC) |  | 0 | ms-coildata |  | wm-wf-3d |  |  | DIS
| simulate operational TF coil cage shape |  | 6 | tfopp |  | ms-coildata |  |  | SCOD
| build 3D TFC field maps + check predictions of first wall field line deviations |  | 6 | baseline-map3d |  | tfopp |  |  | SCOD
| build 3D PF and CS coil field maps + check predictions of overlap error fields |  | 9 | PF-map3d |  | baseline-map3d |  |  | SCOD
| build 3D CC coil field maps + check predictions of corrected field symmetry |  | 6 | cc-coil-map3d |  | PF-map3d |  |  | SCOD
| tune 3D field maps from CC vacuum field measurements |  | 3 | tfmap-validate | A-II
| calculate magnetic axis offset from machine axis |  | 3 | vf-magaxis |  | tfmap-validate
| as-built ELM coil data available |  | 0 | ms-elmf | IC-II
| build 3D ELM coil field maps + check predictions for transient response |  | 9 | elm-response |  | ms-elmf
| develop fast coupled VV-ELM coil transfer functions |  | 12 | elm-tf |  | elm-response
| tune 3D ELM coil field maps from vacuum field measurements |  | 3 | elm-coil-map3d |  | wm-ol-3d |  |  | SCOD
.
dynamic model | task | data assimilation |  | dm
| constrain 2D equilibrium with 1D transport model |  | 6 | tm-trans2d |  | nova
| couple equilibrium solver to transient eddy current and power supply models |  | 6 | nova-eddy |  | nova,wm-2d-tune,tm-trans2d
| transient in-house free-boundary equilibrium solver available |  | 0 | ms-nova-trans |  | nova-eddy
| test eddy current and power supply models |  | 3 | test-nova-eddy | A-II
| constrain 3D equilibrium with 1D transport model |  | 6 | tm-trans3d |  | ms-nova-3d
| benchmark 3D equilibrium + 1D transport model |  | 3 | tm-trans3d-forw |  | tm-trans3d
| coupled 3D equilibrium + 1D transport model available |  | 0 | ms-trans3d |  | tm-trans3d-forw
.
state estimation | task |  |  | cr
| develop Kalman filters for plasma (synthetic mag-only) |  | 7 | pkm-mag2d-plasma |  | tm-trans2d
| develop Kalman filters for passive structure (synthetic mag-only) |  | 9 | pkm-mag2d-wall |  | ms-nova-trans
| implement full state-aware model (plasma + passive structure) |  | 9 | pkm-2d |  | pkm-mag2d-wall,pkm-mag2d-plasma
| Kalman filter data assimilation available (synthetic analysis pipeline) |  | 0 | ms-pkm2d |  | pkm-2d
| apply causal reconstruction workflow in support of first plasma |  | 6 | pkm-fp |  | test-nova-eddy
| develop ensemble Kalman filters for plasma (3D full diagnostic baseline) |  | 3 | pekm-full3d-plasma |  | ms-nova-3d,tm-trans3d-forw
| develop ensemble Kalman filters for plasma and passive structure (3D full diagnostic baseline) |  | 3 | pekm-full3d |  | pekm-full3d-plasma
| 3D causal reconstruction via Kalman filters available |  | 0 | ms-pekm3d |  | pekm-full3d
| apply causal reconstruction workflow in support of PFPO-1 |  | 6 | pekm-3d-pfpo1 |  | ms-pekm3d
| apply causal reconstruction workflow in support of PFPO-2 |  | 12 | pekm-3d-pfpo2 |  | elm-coil-map3d
.
stability analysis | task | stability |  | sta
| calculate positions of low-n rational surfaces (synthetic input) |  | 9 | sta-rational |  | pkm-2d
| validate positions of low-n rational surface on RTN |  | 6 | sta-rational-val |  | sta-rational
| calculate proximity to ideal low-n linear stability in 2d equilibrium |  | 12 | sta-proxy-2d |  | sta-rational-val
| baseline low-n stability metrics available |  | 0 | ms-sta-low-n |  | sta-proxy-2d
| establish need for automatic stability post-processing vs user-triggered |  | 4 | sta-automatic |  | ms-sta-low-n
| calculate resistive low-n stability (NTMs) |  | 9 | sta-NTMs |  | pkm-fp
| establish need to provide information on other stability boundaries |  | 4 | sta-other |  | sta-NTMs
| establish if routine high-n peeling / ballooning stability is viable / required |  | 6 | sta-high-n |  | sta-other
| calculate high-n peeling / ballooning stability (ELMs) |  | 6 | sta-ELMs |  | elm-coil-map3d,sta-high-n
| assess need for higher-n calculations of AE modes (advanced control) |  | 9 | sta-AE |  | pekm-3d-pfpo1
| calculate resistive low-n stability (NTMs) including TBMs |  | 6 | sta-NTMs-TBM |  | sta-AE
| calculate proximity to ideal low-n linear stability in 3d equilibrium |  | 9 | sta-proxy-3d |  | sta-NTMs-TBM
.