## Sheet1
task | subtask | label | before | after | start | end | duration | responsible
assembly | phase | PFP | FP |  |  |  | 36 | IO
first plasma | phase | FP |  | PFP | 2025-12-01 |  | 18 | IO
pre full power operation 1 | phase | PFPO1 |  | FP |  |  | 18 | IO
pre full power operation 2 | phase | PFPO2 |  | PFPO1 |  |  | 21 | IO
full power operation 1 | phase | FPO1 |  | PFPO2 |  |  | 24 | IO
full power operation 2 | phase | FPO2 |  | FPO1 |  |  | 24 | IO
full power operation 3 | phase | FPO3 |  | FPO2 |  |  | 24 | IO
.
3D vacuum field | task | vf | [5 empty] | DIS,SCOD
| collect as-built TF coil cage geometric data | tff |  | PFP |  |  |  | DIS
| collect as-built central solenoid geometric data | csf |  | PFP |  |  |  | DIS
| collect as-built PFC geometric data | pff |  | PFP |  |  |  | DIS
| simulate operational TF coil cage shape | tfopp |  | PFP,tff |  |  |  | SCOD
| check field symetry + build 3D field maps | map3D |  | tfopp |  |  |  | SCOD
.
diagnostics | task | diag | [5 empty] | IVD
| commission magnetics-only diagnostics | mag-only |  | PFP |  |  | 2 | IVD
| magnetics-only inferance (Bayesian) | mag-bay |  | mag-only,tfopp |  |  | 6 | SCOD
| commission MSE diagnostic | MSE |  | FP |  |  | 2 | IVD
| commission full baseline diagnostic set | diag-full |  | MSE,PFPO1
.
wall model | task | wm
| develop 2D wall model (eddy current) | wm-2d-eddy
| validate 2D using synthetic + Alcator-C mod data | wm-2d-val
| develop 3D wall model (eddy current) | wm-3d-eddy
| validate 3D using synthetic + Alcator-C mod data | wm-3d-val
| check commissioning limits for coils and power supplies | cps | FP
| generate broadband commissioning waveforms | wm-wf |  | cps
| mesure open-loop vessel response | wm-ol |  | wm-wf
| calibrate 2D wall model | wm-2d-cal |  | wm-ol
| calibbrate 3D wall model | wm-3d-cal |  | wm-ol,wm-2d-cal
.
ferritic model | task | fm
| defeature ferritic insert geometry - store in IMAS | fm-geom | PFP
| develop dipole representation (fast, far-field) | fm-dipole |  | fm-geom
| update ferritic geometry based on mesurments (Bayesian) | fm-bay |  | fm-geom,mag-bay
.
linear reconstruction | task | lr
| transfer existing 2D codes to IMAS (EFIT++, PEFIT, LUCIE) | lin-code2d | PFP |  |  |  |  | SCOD,CCFE,F4E
| benchmark (synthetic mag-only) | lin-bm-mag |  | lin-code2d |  |  |  | SCOD,F4E
| benchmark (synthetic mag + MSE) | lin-bm-MSE |  | lin-bm-mag
| benchmark (synthetic full diagnostic baseline) | lin-bm-full |  | lin-bm-MSE
| benchmark (machine(s) full avalible) | lin-bm-machine |  | lin-bm-full
| code improvement (GPU / refactoring) | lin-refactor |  | lin-bm-mag,lin-bm-MSE,lin-bm-full
| check exisiting code convergence (mag constraint / shifted grids) | lin-conv |  | lin-code2d
| code improvement (GS convergence - Newtons method) | lin-convNM |  | lin-conv
| transfer existing 3D codes to IMAS (CLISTE) | lin-code3d | FP |  |  |  |  | SCOD
.
plasma state estimation | task | pse
| develop Kalman filters for plasma (mag-only 2D) | pkm-mag2d | FP
| develop Kalman filters for plasma (mag-only + MSE 2D) | pkm-MSE2d |  | pkm-mag2d
| develop Kalman filters for plasma (full diagnostics 2D) | pkm-full2d |  | pkm-MSE2d
| implement full state-aware model (plasma+passive, 2D) | sam2d |  | pkm-full2d
| develop ensemble Kalman filters for plasma (3D) | pekm-full3d |  | sam2d
| implement full state-aware model (plasma+passive, 3D) | sam3d |  | pekm-full3d
.
non-linear reconstruction | task | nlr
| define minimization objective(s) (minimum free-energy,.. ?) | nlr-obj | PFPO1
| develop generic paramitrizations (flux functions) | nlr-param
| deploy 2D | nlr-2d
| deploy 3D | nlr3d
| refactor for real-time / feedback paramitrizations to linear model | nrl-refactor