## Sheet1
task | subtask | duration | label | before | after | start | end | responsible
phase | assembly | 51 | A-I | IC-I
phase | integrated commissioning | 14 | IC-I | FP
phase | phase | 6 | FP |  |  | 2028-12-01
phase | assembly | 24 | A-II |  | FP
phase | integrated commissioning | 6 | IC-II |  | A-II
phase | phase | 18 | PFPO-1 |  | IC-II
phase | assembly | 15 | A-III |  | PFPO-1
phase | integrated commissioning | 9 | IC-III |  | A-III
phase | phase | 21 | PFPO-2 |  | IC-III
phase | assembly | 13 | A-IV |  | PFPO-2
phase | integrated commissioning | 8 | IC-IV |  | A-IV
phase | phase | 16 | FPO-1 |  | IC-IV
phase | shutdown | 8 | SD-I |  | FPO-1
phase | phase | 16 | FPO-2 |  | SD-I
phase | shutdown | 8 | SD-II |  | FPO-2
phase | phase | 16 | FPO-3 |  | SD-II
phase | shutdown | 9 | SD-III |  | FPO-3
phase | phase | 16 | FPO-4 |  | SD-III
phase | shutdown | 8 | SD-IV |  | FPO-4
phase | phase | 16 | FPO-5 |  | SD-IV
phase | shutdown | 4 | SD-V |  | FPO-5
phase | phase | 16 | FPO-6 |  | SD-V
.
equilibrium generation | task |  | eg
| identify and develop IMAS equilibrium tools (flux mapping and transforms) | 6 | nova-map | nova
| adapt in-house 2D free-boundary GS solver to IMAS | 6 | nova | A-I
| adapt external 2D codes to IMAS | 9 | lin-code2d |  | nova
| verify implementation of in-house 2D solver against external codes | 3 | lin-verify |  | lin-code2d
| in-house free-boundary equilibrium solver available | 0 | ms-nova |  | lin-verify
| couple in-house code to transient eddy current and power supply models | 6 | nova-eddy |  | lin-verify
| tune 2D wall model using 3D disruption simulations (Maxwell / Ansys) | 3 | nova-3D-eddy |  | nova-eddy
| transient in-house free-boundary equilibrium solver available | 0 | ms-nova-trans |  | nova-3D-eddy
| establish need for in-house 3D equilibrium generation capability | 3 | nova-3D-GS-need |  | FP
| develop in-house 3D free-boundary GS solver | 18 | nova-3D-GS |  | nova-3D-GS-need
| verify implementation of in-house 3D solver against external codes | 6 | nova-3D-GS-verify |  | nova-3D-GS
| 3D in-house free-boundary equilibrium solver available | 0 | ms-nova-3d |  | nova-3D-GS-verify
.
linear reconstruction | task |  | lr
| develop benchmarks and quality metrics | 3 | lin-metric | lin-bm-mag | lin-code2d
| benchmark (synthetic mag-only) | 6 | lin-bm-mag | ms-lin-code2d-bm | lin-code2d,sdiag-FP,lin-metric |  |  | F4E
| benchmarked real-time codes available on SDCC | 0 | ms-lin-code2d-bm | lin-bm-initial-kinetic | lin-bm-mag
| benchmark (synthetic mag-only + initial kinetic) | 6 | lin-bm-initial-kinetic | lin-bm-full | lin-code2d,sdiag-PFPO-1,lin-bm-mag
| benchmark (synthetic full diagnostic baseline) | 9 | lin-bm-full | lin-bm-full-real | lin-code2d,sdiag-PFPO-2,lin-bm-initial-kinetic
| benchmark (experimental no other tokamaks, full diagnostic baseline) | 9 | lin-bm-full-real | ms-lin-code-rt2d | lin-bm-full
| select real-time 2D reconstruction code and make available on SDCC | 0 | ms-lin-code-rt2d | lin-conv | lin-bm-full-real
| check existing code convergence (mag constraint / shifted grids) | 3 | lin-conv | lin_recon | lin-bm-full-real
| investigate use of non-standard diagnostics (vessel strain and displacement) | 3 | lin-strain |  | FP
| extend in-house code to use vv structural diagnostics | 9 | lin-strain-nova |  | lin-strain
| separation of plasma and vessel current in advance of kinetic measurements | 0 | ms-lin-strain-nova |  | lin-strain-nova
| perform low current equilibrium reconstructions (online + offline codes) | 6 | lin_recon |  | IC-I
| code refactoring to improve performance and physics fidelity | 9 | lin-refactor |  | lin_recon
| adapt 3D codes to IMAS | 18 | lin-code3d |  | lin-refactor |  |  | SCOD
| 3D reconstruction codes available on SDCC | 0 | ms-lin-code3d |  | lin-code3d
.
non-linear reconstruction | task |  | nlr
| define minimization objective(s) (minimum free-energy) | 6 | nlr-obj | PFPO-1
| develop generic parametrizations (flux functions) | 9 | nlr-param |  | nlr-obj
| refactor non-linear search for real-time (ML model) | 18 | nlr-refactor |  | nlr-param
| couple non-linear search algorithms (optimizers) to 2D code | 9 | nlr-opp-2d |  | nlr-refactor
| commission 2D non-linear reconstruction | 6 | nlr2d |  | nlr-opp-2d
| non-linear 2D reconstructions available | 0 | ms-nlr2d |  | nlr2d
| couple non-linear search algorithms (optimizers) to 3D code | 3 | nlr-opp-3d |  | ms-nlr2d
| commission 3D non-linear reconstruction | 6 | nlr3d |  | nlr-opp-3d
| non-linear 3D reconstructions available | 0 | ms-nlr3d |  | nlr3d
.
ferritic model | task |  | fm
| extend IMAS data dictionary to represent ferritic structures | 3 | fm-imas | fm-geom
| implement ferritic insert geometry in IMAS | 3 | fm-geom | fm-dipole
| develop dipole representation (fast, far-field) | 9 | fm-dipole | fm-tbm
| implement ferritic TBM geometry in IMAS | 6 | fm-tbm | fm-dipole-tbm
| extend dipole representation to include TBMs | 12 | fm-dipole-tbm | IC-I
| update insert geometry from measurements | 9 | fm-bay | FP
| ferritic insert model available | 0 | ms-ferritic-inserts |  | fm-bay
| update TBM geometry from measurements | 9 | fm-tbm-bay | PFPO-2 | fm-dipole-tbm,diag-full-tbm
| ferritic TBM model available | 0 | ms-ferritic-tbm |  | fm-tbm-bay
.
wall model | task |  | wm
| develop 2D model (eddy current) | 9 | wm-2d-eddy | wm-2d-val | fm-dipole
| validate 2D model using Alcator-C mod data | 6 | wm-2d-val | wm-wf | wm-2d-eddy,sdiag-FP
| validate / develop 2D magnet commissioning waveforms | 9 | wm-wf | IC-I
| measure open-loop vessel response (2D model) | 6 | wm-ol | FP | wm-wf,mag-only-bay
| tune 2D wall model | 6 | wm-2d-cal |  | wm-ol
| slow transient 2D model available | 0 | ms-wm-2d-slow |  | wm-2d-cal
| tune model to fit disruption behaviour (low current) | 9 | wm-disrupt-low |  | IC-I,wm-2d-cal
| fast transient 2D model available (low current) | 0 | ms-wm-2d-fast |  | wm-disrupt-low
| develop 3D wall model (eddy current ) | 3 | wm-3d-eddy |  | ms-wm-2d-fast
| validate 3D wall model on Alcator-C mod data | 3 | wm-3d-val |  | wm-3d-eddy
| develop 3D magnet commissioning waveforms (ELM) | 9 | wm-wf-3d |  | wm-3d-val
| measure open-loop vessel response (3D model) | 6 | wm-ol-3d |  | wm-wf-3d
| tune model to fit disruption behaviour (half current) | 6 | wm-disrupt-half |  | wm-ol-3d
| fast transient 2D model available (half current) | 0 | ms-wm-2d-fast-half |  | wm-disrupt-half
| develop 2D shield-block models | 3 | wm-shield |  | PFPO-1
| develop 3D shield-block models | 9 | wm-shield-3d |  | wm-shield
| develop 3D magnet commissioning waveforms (full current) | 9 | wm-wf-shield-3d |  | wm-shield-3d
| tune 2D and 3D models to fit disruption behaviour (full current) | 6 | wm-ol-3d-fast |  | wm-wf-shield-3d
| fast transient 3D model available + shield-blocks (full current) | 0 | ms-wm-ol-3d |  | wm-ol-3d-fast
.
vacuum field | task |  | vf |  |  |  |  | DIS,SCOD
| as-built coil cage geometric data available (TFC, PFC, CS) | -24 | ms-coildata |  | A-I |  |  | DIS
| simulate operational TF coil cage shape | 3 | tfopp |  | ms-coildata |  |  | SCOD
| build 3D field maps + check toroidal field symmetry | 9 | baseline-map3d |  | tfopp |  |  | SCOD
| as-built correction coil geometric data available | 9 | ms-ccf | IC-I
| build 3D correction coil field maps + check corrected field symmetry | 9 | cc-coil-map3d |  | ms-ccf |  |  | SCOD
| TF mapping diagnostic data available | 0 | ms-tfmap | FP
| validate / develop 3D field maps | 9 | tfmap-validate |  | ms-tfmap
| as-built ELM coil data available | 12 | ms-elmf |  | IC-I
| build 3D ELM coil field maps | 9 | elm-coil-map3d |  | ms-elmf |  |  | SCOD
| ELM coils installed | 0 | ms-elm-install |  | A-II
| validate / develop 3D field maps including ELM coil operation | 18 | elm-data |  | ms-elm-install
.
synthetic diagnostics | task |  | sdiag
| FP diagnostic forward models | 18 | sdiag-FP | A-I
| PFPO-1 diagnostic forward models | 18 | sdiag-PFPO-1 | FP
| PFPO-2 diagnostic forward models | 18 | sdiag-PFPO-2 | PFPO-1
| full set of synthetic diagnostics available | 0 | ms-sdiag |  | sdiag-PFPO-2
.
diagnostic feed pre-processing | task |  | diag |  |  |  |  | IVD
| validate / develop magnet commissioning waveforms | 9 | diag-wf | IC-I
| magnetics-only diagnostics available | 0 | ms-mag-only |  | A-I
| magnetics-only inference (vacuum field) | 9 | mag-only-bay |  | diag-wf |  |  | SCOD
| magnetics-only inference (low current) | 6 | mag-only-fp | A-II
| (DIP, TIP, TS core r/a<85%) available | 6 | ms-kinetic1 |  | IC-II |  |  | IVD
| initial kinetic inference | 9 | kinetic1-bay |  | ms-kinetic1
| develop commissioning waveforms to target TBMs | 12 | wm-wf-tbm | PFPO-2
| re-calibrate diagnostics following TBM installation | 9 | diag-full-tbm |  | wm-wf-tbm
| (PoPola, MSE-LS, TS edge, Reflectometry) available | 9 | ms-diag-full |  | IC-III
| full baseline diagnostics inference | 6 | diag-full-bay |  | ms-diag-full
| full baseline diagnostics inference + TBM | 5 | diag-full-tbm-bay |  | fm-dipole-tbm,diag-full-bay
.
transport model | task |  | tm
| constrain 2D equilibrium with 1D transport model | 9 | tm-trans2d |  | A-I
| benchmark 2D equilibrium + 1D transport model | 6 | tm-trans2d-forw |  | IC-II
| coupled 2D equilibrium + 1D transport model available | 0 | ms-trans2d |  | tm-trans2d-forw
| constrain 3D equilibrium with 1D transport model | 9 | tm-trans3d | IC-III | ms-lin-code3d
| benchmark 3D equilibrium + 1D transport model | 12 | tm-trans3d-forw |  | tm-trans3d,PFPO-1,IC-III
| coupled 3D equilibrium + 1D transport model available | 0 | ms-trans3d |  | tm-trans3d-forw
.
kalman filter | task |  | pkm
| develop Kalman filters for plasma (mag-only 2D) | 6 | pkm-mag2d |  | tm-trans2d
| develop Kalman filters for plasma (mag-only + initial kinetic 2D) | 9 | pkm-initial-kinetic2d |  | pkm-mag2d
| develop Kalman filters for plasma (full diagnostics 2D) | 6 | pkm-full2d |  | pkm-initial-kinetic2d
| implement full state-aware model (plasma+passive, 2D) | 9 | pkm-2d |  | pkm-full2d,ms-trans2d
| 2D plasma Kalman filter available | 0 | ms-pkm2d |  | pkm-2d
| develop ensemble Kalman filters for plasma (3D) | 18 | pekm-full3d |  | ms-pkm2d
| implement full state-aware model (plasma+passive, 3D) | 6 | pekm-3d |  | tm-trans3d-forw,pekm-full3d
| 3D plasma Kalman filter available | 0 | ms-pekm3d |  | pekm-3d
.
stability analysis | task |  | sta
| calculate positions of low-n rational surfaces (synthetic input) | 9 | sta-rational | FP
| validate positions of low-n rational surface on RTN | 3 | sta-rational-val |  | sta-rational
| calculate proximity to ideal low-n linear stability in 2d equilibrium | 9 | sta-proxy-2d |  | sta-rational-val
| baseline low-n stability metrics available | 0 | ms-sta-low-n |  | sta-proxy-2d
| establish need for automatic stability post-processing vs user-triggered | 6 | sta-automatic |  | ms-sta-low-n
| calculate resistive low-n stability (NTMs) | 9 | sta-NTMs |  | ms-ferritic-inserts,sta-automatic
| establish need to provide information on other stability boundaries | 3 | sta-other |  | sta-NTMs
| establish if routine high-n peeling / ballooning stability is viable / required | 6 | sta-high-n |  | lin-code3d,sta-other
| calculate high-n peeling / ballooning stability (ELMs) | 9 | sta-ELMs |  | elm-coil-map3d,sta-high-n
| assess need for higher-n calculations of AE modes (advanced control) | 9 | sta-AE | IC-III
| calculate resistive low-n stability (NTMs) including TBMs | 6 | sta-NTMs-TBM |  | ms-wm-ol-3d,IC-III
| calculate proximity to ideal low-n linear stability in 3d equilibrium | 9 | sta-proxy-3d |  | sta-NTMs-TBM
.