## Sheet1
task | subtask | label | prerequisite | start | end | duration
3D vacuum field | * | vf
| collect as-built TF coil cage geometric data | tff
| collect as-built central solenoid geometric data | csf
| collect as-built PFC geometric data | pff
| simulate operational TF coil cage shape | tfopp | tff
wall model | * | wm
| check commissioning limits for coils and power supplies | cps
| generate broadband commissioning waveforms |  | cps
diagnostics
plasma state estimation
develop Kalman filters for plasma
implement full state-aware model
linear reconstruction
transfer existing codes to IMAS
check exicution speed
code improvement (GPU / refactoring)
non-linear reconstruction
Define minimization objective(s) (free-energy)
Develop generic paramitrizations
Deploy 2D
Deploy 3D - ensemble Kalman filter
Make real-time / feedback paramitrizations to linear model